## Dashboard
Azure Windows VM Terraform Project Dashboard
Health
Overall Progress |  | Budget Utilized | Schedule |  | Quality |  |  | Scope
55% |  | 48% | 62% |  | 58% |  |  | Schedule
Risk
Quality
Project Timeline |  |  |  | Executive Gauge
Phase | Start Day | Duration |  | Overall Progress | 55 | Target | 100
Planning | 1 | 2
Design | 3 | 2
Implementation | 5 | 5
Testing | 10 | 3
Documentation | 13 | 2

## WBS
Project: Deploy and Manage an Azure Windows Virtual Machine using Terraform
Project Start Date | 29/06/2026 | ONDC APP Infra | Not Started | 29/06/2026
Project End Date | 2026-10-06 |  | In-Progress | 2026-10-06
Project Status | On-Time |  | Completed | On-Time
Epic / Milestone | Task | Subtask | Dependency | Deliverable | Status | Remark
1. Project Planning | Review Requirements | Understand project objectives and expected outcomes | None | Requirement document reviewed
| Prepare Development Environment | Install Terraform, Azure CLI, Visual Studio Code, authenticate using az login | Review Requirements | Development environment ready
| Create Project Structure | Create Terraform project folders and files (main.tf, variables.tf, outputs.tf, terraform.tfvars) | Environment Ready | Project structure created
2. Infrastructure Design | Design Network Architecture | Identify Resource Group, VNet, Subnet, NSG, Public IP, NIC and VM relationships | Planning | Architecture documented
| Define Variables | Identify reusable variables (VM Name, Location, Username, Password, VM Size, Tags) | Project Structure | Variable definitions completed
| Plan Resource Dependencies | Identify Terraform resource dependencies | Design Network | Deployment sequence documented
3. Infrastructure Implementation | Create Resource Group | Deploy Resource Group | Design Complete | Resource Group created
| Create Virtual Network | Create Virtual Network and Subnet | Resource Group | Network deployed
| Configure Security | Create NSG and allow RDP (3389) and HTTP (80); associate NSG | Virtual Network | Network secured
| Configure Networking | Create Public IP and Network Interface | NSG | Network Interface ready
| Deploy Windows VM | Create Windows Server 2022 VM | NIC | VM deployed
| Install IIS | Use VM Extension to install IIS automatically | VM Created | IIS installed
| Verify Web Server | Browse to the VM Public IP and confirm IIS webpage loads | IIS Installed | IIS accessible
| Create Managed Disk | Create a 32 GB Standard HDD managed disk | VM Created | Managed disk created
| Attach Managed Disk | Attach the managed disk to the VM | Managed Disk | Data disk attached
| Resize VM | Change VM size (e.g., Standard_B2s → Standard_D2s_v5) | VM Created | VM resized
| Apply Resource Tags | Apply common tags to all Azure resources | Resources Created | Resources tagged
| Create Outputs | Display VM Name, Public IP, Resource Group and Admin Username | Deployment Complete | Outputs displayed
4. Validation & Testing | Validate Terraform Deployment | Execute terraform plan and terraform apply successfully | Implementation | Successful deployment
| Validate Azure Resources | Verify VM, Disk, NSG, Public IP, and Tags in Azure Portal | Deployment | Azure resources verified
| Validate IIS | Confirm the IIS webpage is accessible over HTTP | NSG & IIS | Website accessible
| Validate Data Disk | Verify attached disk inside Azure Portal (or within the VM) | Disk Attached | Disk available
| Validate VM Resize | Confirm updated VM size in Azure Portal | VM Resized | VM size updated
5. Documentation & Delivery | Capture Screenshots | Capture screenshots of deployed resources, IIS webpage, attached disk, and VM size | Testing | Evidence collected
| Organize Terraform Code | Ensure code is modular, formatted, and documented | Implementation | Well-structured project
| Submit Project | Submit Terraform files and screenshots | Documentation | Final submission completed
6. Cleanup (Optional) | Destroy Infrastructure | Execute terraform destroy | Project Complete | Azure resources removed

## Risk
Risk Register – Azure Windows VM Deployment using Terraform
Risk ID | Risk Description | Category | Probability | Impact | Mitigation Strategy | Contingency Plan | Owner | Status
R-001 | Terraform is not installed or configured correctly | Technical | Medium | High | Verify Terraform installation before starting | Reinstall Terraform and validate using terraform version | Infra Team | Open
R-002 | Azure CLI authentication fails (az login) | Technical | Medium | High | Authenticate before deployment and verify subscription | Re-authenticate or switch subscription | Infra Team | Open
R-003 | Insufficient Azure subscription permissions | Security | Low | High | Verify Contributor access before deployment | Contact Azure Administrator | Infra Team | Open
R-004 | Resource names are not globally unique (Public IP, Storage Account, etc.) | Technical | Medium | Medium | Follow Azure naming conventions and use unique names | Rename the resource and redeploy | Infra Team | Open
R-005 | Terraform syntax errors prevent deployment | Technical | Medium | High | Run terraform fmt and terraform validate before applying | Correct errors and rerun deployment | Infra Team | Open
R-006 | Required Azure resources fail to deploy due to incorrect dependencies | Technical | Medium | High | Define proper Terraform resource references | Review dependency chain and rerun | Infra Team | Open
R-007 | NSG rules are missing or incorrect, blocking RDP or HTTP | Configuration | Medium | High | Configure inbound rules for ports 3389 and 80 | Update NSG rules and reapply Terraform | Infra Team | Open
R-008 | IIS installation fails on the VM | Configuration | Medium | Medium | Use the correct VM Extension or PowerShell script | Re-run the extension or install IIS manually | Infra Team | Open
R-009 | Managed disk fails to attach to the VM | Technical | Low | Medium | Verify disk configuration and LUN assignment | Recreate and reattach the disk | Infra Team | Open
R-010 | VM resize operation fails because the selected size is unavailable in the region | Azure Platform | Medium | Medium | Verify available VM sizes before resizing | Choose another supported VM size | Infra Team | Open
R-011 | Terraform state file becomes corrupted or is deleted | Technical | Low | High | Store the state file safely or use a remote backend | Restore from backup or re-import resources | Infra Team | Open
R-012 | Unexpected Azure costs due to resources not being deleted | Financial | Medium | High | Destroy resources after project completion | Execute terraform destroy and verify deletion | Infra Team | Open
R-013 | Incorrect administrator credentials prevent VM login | Configuration | Low | Medium | Validate username and password before deployment | Redeploy VM with corrected credentials | Infra Team | Open
R-014 | Internet connectivity issues interrupt deployment | External | Low | Medium | Ensure a stable internet connection | Resume deployment after connectivity is restored | Infra Team | Open
R-015 | Students modify Azure resources manually, causing Terraform state drift | Configuration | Medium | High | Make all infrastructure changes only through Terraform | Run terraform plan, reconcile drift, or import resources | Infra Team | Open
Top 5 Risks to Monitor
Priority | Risk | Reason
1 | Azure CLI authentication failure | Prevents any Terraform deployment.
2 | Incorrect NSG configuration | Blocks RDP and HTTP access, preventing VM management and IIS validation.
3 | Terraform syntax or validation errors | Stops infrastructure deployment until corrected.
4 | Azure resource naming conflicts | Common issue, especially with globally unique resource names.
5 | Resources not destroyed after testing | Can lead to unnecessary Azure costs if left running.

## Team
Team Composition and Responsibilities
Role | Team Member(s) | Key Responsibilities | Deliverables
Project Manager | 1 | Plan project activities, assign tasks, monitor progress, manage risks, ensure deadlines are met, coordinate team communication | Project plan, progress tracking, risk register
Cloud Infrastructure Engineer | 1 | Design and deploy Azure infrastructure using Terraform, create Resource Group, VNet, Subnet, Public IP, NIC, and VM | Terraform code for Azure infrastructure
Terraform Developer | 1 | Develop reusable Terraform modules, variables, outputs, tagging strategy, and manage state | Well-structured Terraform code
System Administrator | 1 | Configure Windows Server, install IIS, validate VM accessibility, verify attached disks, perform VM resizing | Configured Windows VM and IIS website
Network & Security Engineer | 1 | Configure NSG rules, verify RDP (3389) and HTTP (80) access, validate network connectivity | Secure networking configuration
Quality Assurance (QA) Engineer | 1 | Test Terraform deployment, validate Azure resources, verify IIS, confirm VM resize and disk attachment | Test report and validation checklist
Documentation Lead | 1 | Prepare project documentation, architecture diagram, screenshots, deployment guide, and final report | Project documentation and user guide

## RACI
Responsibility Matrix
Activity | PM | Cloud Engineer | Terraform Developer | Sys Admin | Security Engineer | QA | Documentation
Project Planning | ✔ | [5 empty] | ✔
Design Architecture | ✔ | ✔ | ✔ |  | ✔ |  | ✔
Create Networking |  | ✔ | ✔ |  | ✔
Deploy Windows VM |  | ✔ | ✔
Install IIS |  |  |  | ✔
Configure NSG |  | ✔ |  |  | ✔
Create & Attach Disk |  | ✔ | ✔ | ✔
Resize VM |  | ✔ | ✔ | ✔
Apply Tags |  |  | ✔
Testing & Validation |  |  |  | ✔ | ✔ | ✔
Documentation | [6 empty] | ✔
Final Project Submission | ✔ | [5 empty] | ✔

## UAT
User Acceptance Testing (UAT) Plan
Test ID | Requirement | Test Steps | Expected Result | Status
UAT-001 | Resource Group Creation | Verify the Resource Group in the Azure Portal | Resource Group exists in the correct region | Pass / Fail
UAT-002 | Virtual Network | Verify VNet and Subnet configuration | VNet and Subnet are created with the correct address space | Pass / Fail
UAT-003 | Network Security Group | Verify NSG rules | Ports 3389 and 80 are allowed | Pass / Fail
UAT-004 | Public IP | Verify Public IP assignment | VM has a Public IP address | Pass / Fail
UAT-005 | Windows VM Deployment | Verify VM status | VM is in Running state | Pass / Fail
UAT-006 | Remote Desktop | Connect to the VM using RDP | Successful login using administrator credentials | Pass / Fail
UAT-007 | IIS Installation | Open http://<Public-IP> in a browser | Default IIS webpage is displayed | Pass / Fail
UAT-008 | Data Disk | Verify attached managed disk | 32 GB Standard HDD is attached to the VM | Pass / Fail
UAT-009 | VM Resize | Verify VM size | VM reflects the updated size (e.g., Standard_D2s_v5) | Pass / Fail
UAT-010 | Resource Tags | Verify tags on Azure resources | Required tags are applied to all resources | Pass / Fail
UAT-011 | Terraform Outputs | Execute terraform output | Outputs display VM Name, Public IP, Resource Group, etc. | Pass / Fail
UAT-012 | Terraform Validation | Execute terraform plan | No unexpected infrastructure changes are detected | Pass / Fail

## CR
Change Request Register
CR | Description | Impact | Approval
CR-001 | Add Managed Disk | Medium | Approved
CR-002 | Resize VM | Medium | Approved
CR-003 | Add Resource Tags | Low | Approved

## Issues Log
Issue Log
ID | Issue | Priority | Owner | Status
I-001 | Azure Authentication Error | High | Cloud Engineer | Open
I-002 | VM Resize Failed | Medium | System Admin | Closed